## Xiang Chen
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 6 | 4 | 2 | discuss initial plan | 2 | 1 |  |  |  | 1 |  | 0,2,5,6 | 10 | Xiang Chen
12/09 - 19/09 | 10 | 6 | 4 | 1,5,0 writing initial plan and prepare for presentation | 2 | 2 | 1 |  |  | 1 |  |  | 10 | Xiang Chen
20/09 - 26/09 | 10 | 8 | 2 | discuss initial plan; set up configuration; teach team members about using git and github; make powerpoint; set up git hub ; set up MAMP for local test; learn php and phpMyAdmin | 1 | 1 | 1 |  | 2 | 2 | 1 | 1,2,3,5 | 10 | Xiang Chen
27/09-04/10 | 12 | 10 | 2 | register domain name; set up web site host; deploy our website on the host; code review; pair programming; handle github pull request; wirte weekly meeting report; discuss about the front-end web design; create user story on the pivottracker; | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 0,1,2,4 | 10 | xiang chen
05/10 - 18/10 | 10 | 8 | 0 | create issue on github; make code change about the front-end; create sql file and upload to github; write user story on the pivot tracker; learning php language solve domain issue | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1,2,3,4 | 10

## Weicheng Yu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 5 | 1 | 4 | discuss initial plan | 1 | 1 | 0.5 | 0 | 0 | 1.5 | 0 |  | 4
12/09 - 19/09 | 6 | 4 | 2 | 0,1,2 ,5, 6 Writing SPPP Draft; Learning PHP and SQL security; Discusing requirements and features | 2 | 1 | 1 | 0 | 0 | 2 | 0 | SPPP Final Draft; Presentation; | 10
20/09 - 26/09 | 8 | 6 | 2 | 0, 1, 2, 5, 6 Finalizing SPPP; Learning front end security issue; Discussion with Yansen about UI design; | 2 | 1 | 2 | 0 | 0 | 2 | 1 | Inital implementation for Iteration 1 prototype; Security Document; | 8
27/09 - 04/10 | 8 | 6 | 2 | 0, 2, 5, 6 Writing Security Document; Learning php back end security issue; Discussion with Yansen about UI design; | 3 | 0 | 1 | 0 | 0 | 2 | 2 | Implement prototype for interation 1; | 8
05/10 - 11/10 | 8 | 6 | 2 | 0, 1, 2, 3, 5, 6 Assist Yansen about three parts of UI we need for Sprint 1; Learn JQuery and PHP for finishing three User Stories; Choose three User Stories as Sprint 1 objective; | 1 | 1 | 1 | 2 | 0 | 2 | 1 | Prepare PPT for presentation; Finish up implementation for Sprint 1; Host weekly meeting when Dawei is not available | 10
12/10 - 18/10 | 10 | 6 | 4 | 0, 3, 5, 6 Prepare PPT for presentation; Assist Yansen with UI finalization; | 1 | 0 | 0 | 3 | 0 | 4 | 2 | Requirement Anaylze for Sprint 2; Refactor good and bad for Sprint 1; Implementation for Spring 2; Securtiy Learning; | 10

## Yansen Liu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 6 | 2 | 4 | making plan | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 8 |  | Yansen Liu
12/09 - 19/09 | 9 | 5 | 4 | design requirements in SPPP, design app | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 6
20/09 - 26/09 | 7 | 5 | 2 | UI design, practice presentation, SPPP, logo design | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 6
27/09-04/10 | 6 | 6 | 0 | UI design, set MAMP environment | 2 | 1 | 1 | 1 | 0 | 1 | 0 | 6
05/10-11/10 | 9 | 7 | 2 | UI design, front-end review and coding, user story design | 2 | 1 | 1 | 2 | 0 | 1 | 0
12/10-18/10 | 10 | 8 | 4 | prepare for presentation 2, front-end inplementation | 1 | 0 | 1 | 4 | 0 | 2 | 0

## Dawei Li
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 8 | 4 | 4 | 0, gathered the tutorial for learning html, CSS, JQuery learned basic html sytax. Had the ability to create a html and CSS based website. 2, gathered 20+ fun team names and project names online, to inspire myself come up with the project name "return to_powerof_a", and the team name"Hello_world" 5, set up slack channel and github repository. Come up with a github practice that ensures every team member is able to update the code Github practice: update the README.md file with everyone's name and role | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 8
11/09 - 18/09 | 14 | 10 | 4 | 0, learn agile methodology. Find out what risks we will face, including management risks and technical risks. 5, planning communication and management method, based on Scrum methology. Summerize basic concept and methods. | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0
19/09-26/09 | 8 | 6 | 2 | 0, learn Scrum and XP programming methodology 1, analyzed requirements, discussed priority of requirements assign requirements on pivotaltracker set priority to requirements 5, created management plan, set deadline for each iteration 6, do the presentation | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 0
27/09-04/10 | 8 | 6 | 2 | 0,learned how to use MAMP to set up local host and do the test, learned PHP, HTML5, CSS, javascript 1, come up with an aproach to realize the main function we need(how to asign backlogs to each sprint) | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
05/10-11/10 | 8 | 4 | 4 | 1, created user stories and calculate its points draw class diagram and make plan of our project develpment 3, help Weicheng to build the UI by using HTML, CSS connect MySQL with PHP 4, look for PHP unit test module 5, assign works to team members |  | 1 |  | 1 | 1 | 1
12/10-18/10 | 10 | 7 | 3 | 3, programming frontend HTML and backend PHP 5, coordinate team members work flow and plan the development in the big picture |  |  |  | 6 |  | 1

## Yuhao Wu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 5 | 1 | 4 | 0,1,2,5 Gathered for first meeting, discuss the overview of our product.Allocating roles and tasks. Learning about enviroment configuration. | 2 | 0.5 | 1 | 0 | 0 | 1 | 0 | 0,1,2,5 | 8
12/09 - 19/09 | 6 | 2 | 4 | 0,1,2,5 Discuss requirements, designing interface, asking questions about confusing part in order to settle for inplementation | 0.5 | 2 | 0.5 | 0 | 0 | 1 | 0 | 0,1,2,3,5 | 10
20/09 - 26/09 | 5 | 3 | 2 | 1,2,5,6 Preparing presentation, task breakdown for implementation, | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 0,1,2,3,4,5 | 8
27/09 - 4/10 | 6 | 4 | 2 | 0,1,2,3,5 Learning about PHP myadmin, discussing requirements, communicating programming skills, implement some of the simple code and SQL sentences. | 1 | 2 | 1 | 1 | 0 | 1 | 0 | 0,1,2,3,4,5 | 10

## Lu Min
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
12/09 - 19/09 | 10 | 6 | 4 | 0,1,5,6 learn php, learn basic test knowledage, discuss with team members about requirenments. | 3 | 1 |  |  |  | 1 | 1
20/09 - 26/09 | 6 | 4 | 2 | 0,1,5 discuss different project ideas, learn php, learn to use testing tools. | 2 | 1 |  |  |  | 1
27/09 - 04/10 | 7 | 5 | 2 | 0,1,3,5 learn php, learn how to use MAMP to test, programming, discuss and improve features | 2 | 1 |  | 1 |  | 1
05/10 - 11/10 | 10 | 8 | 2 | 0,1,4,5 learn php, unit testing, programming, discuss and get feedback from invited users | 3 | 1 |  |  | 2 | 2
12/10 - 18/10 | 13 | 9 | 4 | 0,1,4,5 write test code, prepare interation one presentation, discuss presentation details, compatibility testing | 2 | 1 |  |  | 5 | 1

## Chen Shou
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
12/09 - 19/09 | 9 | 5 | 4 | 0 - learning the product metrics and process metrics,1 - requirement analysis analyze how the quality metrics should involve and how can every design leader get involved ,2 - design for quality assurance steps and process | 1 | 1 | 2 | 0 | 0 | 1 | 0 | Start backend programming part and revise requirement analysis
20/09 - 26/09 | 8 | 6 | 2 | 0 - learning NoSQL database 1- requirement analysis for database design and backend requirement analysis 2- design UML diagram | 2 | 1 | 2 | 0 | 0 | 2 | 1 | UML diagram finish and database creation | 10
27/09 - 4/10 | 6 | 4 | 2 | 0,1,2,3,5 Learning about PHP myadmin, discussing requirements, communicating programming skills, review and change database diagram and creatre new attributes | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0,2,4,5 | 10
05/10 - 15/10 | 10 | 6 | 0 | revise databse design write user story on the pivot tracker; learning php language solve domain issue | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1,2,3,4 | 10