## Xiang Chen
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 6 | 4 | 2 | discuss initial plan | 2 | 1 |  |  |  | 1 |  | 0,2,5,6 | 10 | Xiang Chen
12/09 - 19/09 | 10 | 6 | 4 | 1,5,0 writing initial plan and prepare for presentation | 2 | 2 | 1 |  |  | 1 |  |  | 10 | Xiang Chen
20/09 - 26/09 | 10 | 8 | 2 | discuss initial plan; set up configuration; teach team members about using git and github; make powerpoint; set up git hub ; set up MAMP for local test; learn php and phpMyAdmin | 1 | 1 | 1 |  | 2 | 2 | 1 | 1,2,3,5 | 10 | Xiang Chen

## Weicheng Yu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 5 | 1 | 4 | discuss initial plan | 1 | 1 | 0.5 | 0 | 0 | 1.5 | 0 |  | 4
12/09 - 19/09 | 6 | 4 | 2 | 0,1,2 ,5, 6 Writing SPPP Draft; Learning PHP and SQL security; Discusing requirements and features | 2 | 1 | 1 | 0 | 0 | 2 | 0 | SPPP Final Draft; Presentation; | 10
20/09 - 26/09 | 8 | 6 | 2 | 0, 1, 2, 5, 6 Finalizing SPPP; Learning front end security issue; Discussion with Yansen about UI design; | 2 | 1 | 2 | 0 | 0 | 2 | 1 | Inital implementation for Iteration 1 prototype; Security Document; | 10

## Yansen Liu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 6 | 2 | 4 | making plan | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 8 |  | Yansen Liu
12/09 - 19/09 | 9 | 5 | 4 | design requirements in SPPP, design app | 1 | 1 | 2 | 0 | 0 | 1 | 0
20/09 - 26/09 | 7 | 5 | 2 | UI design, practice presentation, SPPP, logo design | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 6

## Dawei Li
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 8 | 4 | 4 | 0, gathered the tutorial for learning html, CSS, JQuery learned basic html sytax. Had the ability to create a html and CSS based website. 2, gathered 20+ fun team names and project names online, to inspire myself come up with the project name "return to_powerof_a", and the team name"Hello_world" 5, set up slack channel and github repository. Come up with a github practice that ensures every team member is able to update the code Github practice: update the README.md file with everyone's name and role | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 8
11/09 - 18/09 | 14 | 10 | 4 | 0, learn agile methodology. Find out what risks we will face, including management risks and technical risks. 5, planning communication and management method, based on Scrum methology. Summerize basic concept and methods. | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0
19/09-26/09 | 8 | 6 | 2 | 0, learn Scrum and XP programming methodology 1, analyzed requirements, discussed priority of requirements assign requirements on pivotaltracker set priority to requirements 5, created management plan, set deadline for each iteration 6, do the presentation | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 0

## Yuhao Wu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
04/09 - 11/09 | 5 | 1 | 4 | 0,1,2,5 Gathered for first meeting, discuss the overview of our product.Allocating roles and tasks. Learning about enviroment configuration. | 2 | 0.5 | 1 | 0 | 0 | 1 | 0 | 0,1,2,5 | 8
12/09 - 19/09 | 6 | 2 | 4 | 0,1,2,5 Discuss requirements, designing interface, asking questions about confusing part in order to settle for inplementation | 0.5 | 2 | 0.5 | 0 | 0 | 1 | 0 | 0,1,2,3,5 | 12
20/09 - 26/09 | 5 | 3 | 2 | 1,2,5,6 Preparing presentation, task breakdown for implementation, | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 0,1,2,3,4,5 | 10

## Lu Min
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
12/09 - 19/09 | 10 | 6 | 4 | 0,1,5,6 learn php, learn basic test knowledage, discuss with team members about requirenments. | 3 | 1 |  |  |  | 1 | 1
20/09 - 26/09 | 6 | 4 | 2 | 0,1,5 discuss different project ideas, learn php, learn to use testing tools. | 2 | 1 |  |  |  | 1

## Chen Shou
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
12/09 - 19/09 | 9 | 5 | 4 | 0 - learning the product metrics and process metrics,1 - requirement analysis analyze how the quality metrics should involve and how can every design leader get involved ,2 - design for quality assurance steps and process | 1 | 1 | 2 | 0 | 0 | 1 | 0 | Start backend programming part and revise requirement analysis
20/09 - 26/09 | 8 | 6 | 2 | 0 - learning NoSQL database 1- requirement analysis for database design and backend requirement analysis 2- design UML diagram | 2 | 1 | 2 | 0 | 0 | 2 | 1 | UML diagram finish and database creation | 10